## Sheet1
Task | Description | Duration (Hours) | Roles
1. Create Translation Flowchart Guide | This flowchart shows a step-by-step process to help you understand the network manually. | 176 | Siemens Expert Tech Lead
2. Flowchart Validation | The developer analyzes the flowchart to fully grasp its logic. | 80 | Tech Lead SW Developer
3. Build Symbol Database | Build dictionary tables for symbols against an intermediate layer symbol using seimens manuals | 200 | SW Developer Tech Lead
4. Parser Development | The developer will implement a translator to the intermediate layer of the MSW translator (done by Tamer). | 352 | Tech Lead SW Developer
5. Integration with MSW Translator Solution | The developer will integrate the parser component with the MSW translator intermediate layer. | 88 | Tech Lead SW Developer
Total = 896 Hours
Siemense STL file (.AWL)
Existing MSW XML parser
Excel file with transelated Networks
XML file can be imported to tristation